CHANGE ORDER

No. 2 (Final)

DATE OF ISSUANCE ______________________ 	EFFECTIVE DATE______________________

OWNER St. Charles Parish

CONTRACTOR Sealevel Construction, Inc.

Contract: Thoroughbred Lift Station No. 5931 Renovations and 8-Inch Force Main Addition

Project:	_________________________________________________________

OWNER's Contract No. S100901 	ENGINEER's Contract No. S-108-9

ENGINEER Clarence J. Savoie, III, P.E.

You are directed to make the following changes in the Contract Documents:

- Add the Following Work Items:

  - New Contract Item : 	Add 111 days to contract time.

Reason for Change Order: List a reason for each Line Item listed above.  See attached example on how to fill in this information

  - High river levels in the Mississippi River prohibited work. River level increased above 11+00 MSL for 111 days. Contractor began immediately upon level returning to below 11+00 MSL and completed within the allowed 90 days.

Attachments: (Letter of explanation).

| CHANGE IN CONTRACT PRICE: |  | CHANGE IN CONTRACT TIMES: |
| --- | --- | --- |
| Original Contract Price $ 159,000.00 |  | Original Contract Times: Substantial Completion: June 22, 2011 Ready for final payment: August 6, 2011 90 days |
| Net Increase (Decrease) from previous Change Orders No. 1: $1,100.00 |  | Net change from previous Change Orders No.1 to No. 2 _: Substantial Completion: None Ready for final payment: None_ 0 days |
| Contract Price prior to this Change Order: $160,100.00 |  | Contract Times prior to this Change Order: Substantial Completion: June 22, 2011 Ready for final payment: August 6, 2011 90 |
| Net increase of this Change Order: $ 0.00 |  | Net increase this Change Order: Substantial Completion: September 21, 2011 Ready for final payment: December 23, 2011 111days |
| Contract Price with all approved Change Orders: $160,100.00 |  | Contract Times with all approved Change Orders: Substantial Completion: September 21, 2011 Ready for final payment: December 23, 2011 |

RECOMMENDED:			APPROVED:			ACCEPTED:

By:  _             __________             	By:  _             __________         	By:  _             __________

ENGINEER (Authorized Signature)	  OWNER (Authorized Signature)	  CONTRACTOR(Authorized Signature)

Date:               __________             	Date: _        __________             	Date:

EJCDC 1910-8-B (1996 Edition)

Prepared by the Engineers Joint Contract Documents Committee and endorsed by The Associated General Contractors of America and the Construction Specifications Institute.