## Sheet1
SECTION 00806
CHANGE ORDER
No. 1
DATE OF ISSUANCE: August 20, 2010 |  |  |  | EFFECTIVE DATE: August 20, 2010
OWNER: | St. Charles Parish Department of Waterworks
CONTRACTOR: M.R. Pittman Group, L.L.C.
Contract: | East Bank Water Treatment Plant Upgrade
Project: | East Bank Water Treatment Plant Upgrade
OWNER's Contract No.: |  |  | WWKS-44 | ENGINEER's Contract No.: |  | 89170.1
ENGINEER: |  | Shread-Kuyrkendall & Associates, Inc.
You are directed to make the following changes in the Contract Documents:
Description: Change Order No. 1
Reason for Change Order:
To add walkway and platform tie-ins from new Plant D to older plants (A, B, & C) to reduce trip times for
workers and to adjust contract time due to extensive relocation of infrastructure items, evacuations associated | [6 empty] | 2008-11-13 | 730 | 2010-11-13 | Orig Contr Time
with Valero chemical spill and Hurricane Ida, high river level, and unusally high rainfall totals.
Attachments: (List documents supporting change) | [7 empty] | 140 | 2011-04-02 | # Days Beyond Contract
Atachment No. 1 - Description of Changes
[9 empty] | 870 | Total Contr Time w/ Change Order
CHANGE IN CONTRACT PRICE |  |  |  | CHANGE IN CONTRACT TIMES
Original Contract Price:
26450000 |  |  |  | Original Contract Time: 730 days
Net increase/decrease from previous Change Orders |  |  |  | Net change from previous Change Orders No. 0 to No. 0 :
No. 0 to No. 0 :
0 |  |  |  |  | 0 days
Contract Price prior to this Change Order: |  |  |  | Contract Times prior to this Change Order:
26450000 |  |  |  |  | 730 days
Net increase/decrease of this Change Order: |  |  |  | Net increase/decrease this Change Order:
69196.55 |  |  |  |  | 140 days
Contract price with all approved Change Orders: |  |  |  | Contract Time with all approved Change Orders:
26519196.55 |  |  |  |  | 870 days
RECOMMENDED: |  |  | APPROVED: |  | ACCEPTED:
By:________________________ |  |  | By: ______________________ |  | By:________________________
ENGINEER (Authorized Signature) |  |  | OWNER (Authorized Signature) |  | CONTRACTOR (Authorized Signature)
Date:______________________ |  |  | Date:______________________ |  | Date:_______________________
EJCDC 1910-8-B (1996 Edition)
Prepared by the Engineers Joint Contract Documents Committee and endorsed by The Associated General Contractors of America and the Construction Specifications Institute.
END OF SECTION
00806-1