## Sheet1
ATTACHMENT NO. 1 (PAGE 1 OF 3) - DESCRIPTION OF CHANGES
ST. CHARLES PARISH SUB-AQUEOUS MISSISSIPPI RIVER CROSSINGS
Item No. | Description | Unit | Unit Price | Original Contract |  | Change Order No. 1 |  | Total to Date |  | Increases | Decreases | Deletions | Additions
|  |  |  | Quantity | Cost | Quantity | Cost | Quantity | Cost
1 | Relocation of Infrastructure Items | 100000 | 100000 | 1 | 100000 | - | - | 0.07366 | 7366 |  | 92634
2 | Mobilization (Crossing No. 1) | Lump Sum | 50000 | 1 | 50000 | 0.16 | 7795 | 1.16 | 57795 | 7795
3 | Mobilization (Crossing No. 2) | Lump Sum | 50000 | 1 | 50000 | - | - | 1 | 50000
4 | Temporary Construction Signs and Barricades | Lump Sum | 18000 | 1 | 18000 | - | - | 1 | 18000
5 | Removal of Structures and Obstructions | Lump Sum | 15000 | 1 | 15000 | - | - | 1 | 15000
6 | Clearing (for Entry to Batture) | Lump Sum | 25000 | 1 | 25000 | - | - | 1 | 25000
7 | Removal and Resplacement of Signs | Lump Sum | 15000 | 1 | 15000 | - | - | 1 | 15000
8 | Laydown and Fusing of 24" OD SDR 9 HDPE Water Line | L.F. | 100 | 5800 | 580000 | 507 | 50700 | 6307 | 630700 | 50700
9 | Directional Drill Pilot Hole for 24" OD HDPE on Crossing No. 1 (1st Attempt) | Ea. | 1000 | 1 | 1000 | - | - | 1 | 1000
10 | Directional Drill Pilot Hole for 24" OD HDPE on Crossing No. 1 (2nd Attempt) | Ea. | 50 | 1 | 50 | - | - | 1 | 50
11 | Directional Drill Pilot Hole for 24" OD HDPE on Crossing No. 2 (1st Attempt) | Ea. | 1000 | 1 | 1000 | - | - | 1 | 1000
12 | Directional Drill Pilot Hole for 24" OD HDPE on Crossing No. 2 (2nd Attempt) | Ea. | 50 | 1 | 50 | - | - | 1 | 50
13 | Pull 24" OD SDR 9 HDPE Water Line | L.F. | 295 | 5800 | 1711000 | 507 | 149565 | 6307 | 1860565 | 149565
14 | Jack and Bore 30" Steel Casing | L.F. | 275 | 45 | 12375 | 30 | 8250 | 75 | 20625 | 8250
15 | Directional Drill 22" SDR 11 HDPE Water Line | L.F. | 150 | 100 | 15000 | - | - | 0 | 0 |  |  | 15000
16 | Directional Drill 14" SDR 11 HDPE Water Line | L.F. | 125 | 315 | 39375 | - | - | 100 | 12500 |  | 26875
17 | 18" PVC Water Line | L.F. | 60 | 9650 | 579000 | - | - | 6337 | 380220 |  | 198780
18 | 16" PVC Water Line | L.F. | 50 | 105 | 5250 | - | - | 20 | 1000 |  | 4250
19 | 12" PVC Water Line | L.F. | 30 | 440 | 13200 | - | - | 0 | 0 |  |  | 13200
20 | 10" PVC Water Line | L.F. | 25 | 385 | 9625 | - | - | 380 | 9500 |  | 125
21 | 18" DI Water Line | L.F. | 72 | 890 | 64080 | - | - | 386 | 27792 |  | 36288
22 | 12" DI Water Line | L.F. | 47 | 275 | 12925 | 463 | 21761 | 738 | 34686 | 21761
23 | Class A Structural Concrete | C.Y. | 48 | 400 | 19200 | - | - | 419 | 20112 | 912
24 | 18" PVC 11¼° Bend | Ea. | 1350 | 9 | 12150 | - | - | 7 | 9450 |  | 2700
25 | 18" DI 11¼° Bend | Ea. | 1400 | 10 | 14000 | 3 | 4200 | 13 | 18200 | 4200
26 | 18" PVC 90° Bend | Ea. | 1575 | 1 | 1575 | - | - | 0 | 0 |  |  | 1575
27 | 12" DI 11¼° Bend | Ea. | 500 | 3 | 1500 | 7 | 3500 | 10 | 5000 | 3500
28 | 10" DI 11¼° Bend | Ea. | 440 | 3 | 1320 | - | - | 0 | 0 |  |  | 1320
29 | 10" PVC 22½° Bend | Ea. | 440 | 3 | 1320 | 2 | 880 | 5 | 2200 | 880
30 | 18" DI 45° Bend | Ea. | 10400 | 3 | 31200 | - | - | 3 | 31200
31 | 24" HDPE 11¼° Bend | Ea. | 1225 | 4 | 4900 | - | - | 0 | 0 |  |  | 4900
32 | 22" HDPE 11¼° Bend | Ea. | 1375 | 3 | 4125 | - | - | 0 | 0 |  |  | 4125
33 | 18" DI to 18" PVC Adapter | Ea. | 1295 | 3 | 3885 | - | - | 3 | 3885
34 | 10" DI to 14" HDPE Adapter | Ea. | 1445 | 3 | 4335 | - | - | 3 | 4335
35 | 10" PVC to 14" HDPE Adapter | Ea. | 1400 | 1 | 1400 | - | - | 1 | 1400
36 | 24" HDPE to 18" PVC Adapter | Ea. | 3375 | 7 | 23625 | - | - | 4 | 13500 |  | 10125
37 | 22" HDPE to 18" DI Adapter | Ea. | 3322 | 2 | 6644 | - | - | 0 | 0 |  |  | 6644
38 | 22" HDPE to 18" PVC Adapter | Ea. | 3300 | 2 | 6600 | - | - | 0 | 0 |  |  | 6600
39 | 18" DI to 24" HDPE Adapter | Ea. | 3300 | 3 | 9900 | - | - | 1 | 3300 |  | 6600
ATTACHMENT NO. 1 (PAGE 2 OF 3) - DESCRIPTION OF CHANGES
ST. CHARLES PARISH SUB-AQUEOUS MISSISSIPPI RIVER CROSSINGS
Item No. | Description | Unit | Unit Price | Original Contract |  | Change Order No. 1 |  | Total to Date |  | Increases | Decreases | Deletions | Additions
|  |  |  | Quantity | Cost | Quantity | Cost | Quantity | Cost
40 | 12" PVC to 6" PVC Reducer | Ea. | 415 | 2 | 830 | - | - | 0 | 0 |  |  | 830
41 | 18" PVC to 12" PVC Reducer | Ea. | 1470 | 4 | 5880 | 3 | 4410 | 7 | 10290 | 4410
42 | 18" PVC to 16" PVC Reducer | Ea. | 1547 | 1 | 1547 | 2 | 3094 | 3 | 4641 | 3094
43 | 12" PVC to 10" PVC Reducer | Ea. | 455 | 1 | 455 | - | - | 1 | 455
44 | 12" PVC to 10" DI Reducer | Ea. | 455 | 1 | 455 | - | - | 0 | 0 |  |  | 455
45 | 12" x 10" DI Reducer | Ea. | 445 | 2 | 890 | - | - | 0 | 0 |  |  | 890
46 | 18" x 18" PVC Tee w/Cap | Ea. | 3370 | 1 | 3370 | - | - | 1 | 3370
47 | Removal of Existing 6" CI Water Main | L.F. | 7 | 1700 | 11900 | - | - | 0 | 0 |  |  | 11900
48 | Connection to Newly Installed 18" Water Line | Ea. | 1400 | 1 | 1400 | - | - | 0 | 0 |  |  | 1400
49 | Connection to Existing 16" Water Line | Ea. | 14200 | 2 | 28400 | - | - | 2 | 28400
50 | Connection to Existing 10" Water Line | Ea. | 5700 | 2 | 11400 | - | - | 2 | 11400
51 | Connect New and Exisiting Water Service Connections | Ea. | 1200 | 20 | 24000 | - | - | 0 | 0 |  |  | 24000
52 | 22½° 12" PVC to 12" DI Bend/ Adapter | Ea. | 625 | 1 | 625 | 3 | 1875 | 4 | 2500 | 1875
53 | 11¼° 18" PVC to 18" DI Bend/Adapter | Ea. | 1675 | 2 | 3350 | - | - | 0 | 0 |  |  | 3350
54 | 11¼° 18" PVC to 24" HDPE Bend/Adapter | Ea. | 2000 | 1 | 2000 | - | - | 1 | 2000
55 | 4" Depth Asphalt Roadway and Driveway Repairs | Ton | 20 | 482 | 9640 | - | - | 46.803 | 936.06 |  | 8703.94
56 | 4" Depth Concrete Driveway Repairs | C.Y. | 900 | 4 | 3600 | 3.461 | 3114.9 | 7.461 | 6714.9 | 3114.9
57 | Limestone Driveway (Match Existing Depth) | C.Y. | 75 | 50 | 3750 | - | - | 33.94 | 2545.5 |  | 1204.5
58 | Crushed Stone (for Temporary Levee Access Roads) | C.Y. | 57 | 1300 | 74100 | 130.48 | 7437.36 | 1430.48 | 81537.36 | 7437.36
59 | Embankment (for Levee Crossings and Air Release Valves) | C.Y. | 17 | 11500 | 195500 | 412.4905 | 7012.3385 | 11912.4905 | 202512.3385 | 7012.3385
59 | Emabankment (for Temporary Levee Access Roads) | C.Y. | 15 | 35500 | 532500 | - | - | 23000 | 345000 |  | 187500
60 | Removal of Concrete Slope Paving | C.Y. | 115 | 210 | 24150 | - | - | 10 | 1150 |  | 23000
61 | Replacement of Levee Concrete Slope Paving | C.Y. | 525 | 210 | 110250 | - | - | 10 | 5250 |  | 105000
60 | Removal of 4" Depth Asphalt Bike Path | Tons | 75 | 10 | 750 | 10 | 750 | 20 | 1500 | 750
61 | Replacement of 4" Depth Asphalt Bike Path | Tons | 265 | 10 | 2650 | - | - | 10 | 2650
62 | Fire Hydrants | Ea. | 3000 | 5 | 15000 | - | - | 0 | 0 |  |  | 15000
63 | 10" Panametric Ultrasonic Flowmeter and Box | Ea. | 13200 | 2 | 26400 | - | - | 1 | 13200 |  | 13200
64 | 12" Panametric Ultrasonic Flowmeter and Box | Ea. | 18600 |  |  | 1 | 18600 | 1 | 18600 |  |  |  | 18600
65 | 18" Gate Valve with Valve Box | Ea. | 8700 | 6 | 52200 | - | - | 10 | 87000 | 34800
66 | 16" Gate Valve with Valve Box | Ea. | 5700 | 1 | 5700 | - | - | 0 | 0 |  |  | 5700
67 | 12" Automatic Shut-Off Valve | Ea. | 14000 | - | - | 2 | 28000 | 2 | 28000 |  |  |  | 28000
68 | 3" Crispin Air Relief Valve | Lump Sum | 2415.15 | - | - | 2 | 4830.3 | 2 | 4830.3 |  |  |  | 4830.3
69 | Air Relief Valve Concrete Box | Lump Sum | 5589.48 | - | - | 2 | 11178.96 | 2 | 11178.96 |  |  |  | 11178.96
70 | Concrete Pipe Supports on Top of Levee | Lump Sum | 28251 | - | - | 2 | 56502 | 2 | 56502 |  |  |  | 56502
71 | 12" PVC Restraints | Ea. | 135 | - | - | 40 | 5400 | 40 | 5400 |  |  |  | 5400
ATTACHMENT NO. 1 (PAGE 3 OF 3) - DESCRIPTION OF CHANGES
ST. CHARLES PARISH SUB-AQUEOUS MISSISSIPPI RIVER CROSSINGS
Item No. | Description | Unit | Unit Price | Original Contract |  | Change Order No. 1 |  | Total to Date |  | Increases | Decreases | Deletions | Additions
|  |  |  | Quantity | Cost | Quantity | Cost | Quantity | Cost
72 | 12" PVC Water Line | L.F. | 37.9 | - | - | 176 | 6670.4 | 176 | 6670.4 |  |  |  | 6670.4
73 | 12" DR 11 HDPE Pipe | L.F. | 169 | - | - | 2029 | 342901 | 2029 | 342901 |  |  |  | 342901
74 | 12" Solid Sleeve | Ea. | 735 | - | - | 8 | 5880 | 8 | 5880 |  |  |  | 5880
75 | 12" x 24" DI Reducer | Ea. | 4000 | - | - | 2 | 8000 | 2 | 8000 |  |  |  | 8000
76 | 24" Harvey Adapter | Ea. | 3945 | - | - | 2 | 7890 | 2 | 7890 |  |  |  | 7890
77 | 12" x 12" x 10" Tap Sleeve, Valve, and Box | Ea. | 12596 | - | - | 1 | 12596 | 1 | 12596 |  |  |  | 12596
78 | 12" x 12" x 12" Tap Sleeve, Valve, and Box | Ea. | 12930 | - | - | 1 | 12930 | 1 | 12930 |  |  |  | 12930
79 | 12" Tee | Ea. | 500 | - | - | 4 | 2000 | 4 | 2000 |  |  |  | 2000
|  |  | SUB TOTALS: |  | 4617301 |  |  |  | 4616861.8185 | 310056.5985 | 716985.44 | 116889 | 523378.66
|  |  | RESULTING INCREASE (DECREASE) FOR PROJECT BID: | [6 empty] | -439.1815