## Sheet1
ATTACHMENT NO. 1 (PAGE 1 OF 2) - DESCRIPTION OF CHANGES
EAST BANK WATER TREATMENT PLANT UPGRADE
Item No. | Description | Unit | Unit Price | Original Contract |  | Change Order No. 1 |  | Adjusted Contract |  | Additions
|  |  |  | Quantity | Cost | Quantity | Cost | Quantity | Cost
1 | Temporary Facilities | Lump Sum | 45000 | 1 | 45000 | - | - | 1 | 45000
2 | Project Sign | Ea. | 3500 | 2 | 7000 | - | - | 2 | 7000
3 | Exploratory Excavation | Ea. | 800 | 10 | 8000 | - | - | 10 | 8000
4 | Removal of Structures and Obstructions | Lump Sum | 425000 | 1 | 425000 | - | - | 1 | 425000
5 | Limestone Base | Cu. Yd. | 95 | 600 | 57000 | - | - | 600 | 57000
6 | Earthen Fill | Cu. Yd. | 30 | 600 | 18000 | - | - | 600 | 18000
7 | Sandfill Material | Cu. Yd. | 25 | 600 | 15000 | - | - | 600 | 15000
8 | 12" Square PPC Piles | Lin. Ft. | 50 | 1680 | 84000 | - | - | 1680 | 84000
9 | 14" Square PPC Piles | Lin. Ft. | 40 | 20025 | 801000 | - | - | 20025 | 801000
10 | 16" Square PPC Piles | Lin. Ft. | 55 | 6720 | 369600 | - | - | 6720 | 369600
11 | 12" Diamter Timber Piles | Lin. Ft. | 20 | 11405 | 228100 | - | - | 11405 | 228100
12 | Seeding | Lump Sum | 2000 | 1 | 2000 | - | - | 1 | 2000
13 | Asphaltic Concrete, Base Course, Patching, and Incidental Paving | Lump Sum | 75000 | 1 | 75000 | - | - | 1 | 75000
14 | Sewer Force Main Piping (Complete) | Lump Sum | 15000 | 1 | 15000 | - | - | 1 | 15000
15 | Piping (Complete) | Lump Sum | 1650000 | 1 | 1650000 | - | - | 1 | 1650000
16 | Valves (Complete) | Lump Sum | 565000 | 1 | 565000 | - | - | 1 | 565000
17 | Valve Actuators (Complete) | Lump Sum | 50000 | 1 | 50000 | - | - | 1 | 50000
18 | 20" to 30" DI Vertical Offset | Ea. | 9500 | 4 | 38000 | - | - | 4 | 38000
19 | 20" to 30" DI Horizontal Offset | Ea. | 5500 | 3 | 16500 | - | - | 3 | 16500
20 | 12" to 18" DI Vertical Offset | Ea. | 2200 | 60 | 132000 | - | - | 60 | 132000
21 | 12" to 18" DI Horizontal Offset | Ea. | 535 | 19 | 10165 | - | - | 19 | 10165
22 | 12" to 16" Steel Vertical Offset | Ea. | 1750 | 17 | 29750 | - | - | 17 | 29750
23 | 12" to 16" Steel Horizontal Offset | Ea. | 2550 | 4 | 10200 | - | - | 4 | 10200
24 | 4" to 10" DI Vertical Offset | Ea. | 755 | 4 | 3020 | - | - | 4 | 3020
25 | 4" to 10" DI Horizontal Offset | Ea. | 1900 | 4 | 7600 | - | - | 4 | 7600
26 | 1/2" to 3" Brass Vertical Offset | Ea. | 300 | 3 | 900 | - | - | 3 | 900
27 | 1/2" to 3" Brass Horizontal Offset | Ea. | 300 | 3 | 900 | - | - | 3 | 900
28 | 1" to 4" PVC Vertical Offset | Ea. | 25 | 34 | 850 | - | - | 34 | 850
29 | 1" to 4" PVC Horizontal Offset | Ea. | 25 | 14 | 350 | - | - | 14 | 350
30 | Concrete (Plant Control Building) | Lump Sum | 154000 | 1 | 154000 | - | - | 1 | 154000
31 | Concrete (Chemical Feed Building) | Lump Sum | 75000 | 1 | 75000 | - | - | 1 | 75000
32 | Concrete (Clarifiers and Components) | Lump Sum | 1677065 | 1 | 1677065 | - | - | 1 | 1677065
33 | Concrete (Filters and Components) | Lump Sum | 2950000 | 1 | 2950000 | - | - | 1 | 2950000
34 | Concrete (Support Pads) | Lump Sum | 65000 | 1 | 65000 | - | - | 1 | 65000
35 | Concrete (Miscellaneous) | Lump Sum | 15000 | 1 | 15000 | - | - | 1 | 15000
36 | Masonry (Plant Control Building) | Lump Sum | 575000 | 1 | 575000 | - | - | 1 | 575000
37 | Masonry (Chemical Feed Building) | Lump Sum | 75000 | 1 | 75000 | - | - | 1 | 75000
ATTACHMENT NO. 1 (PAGE 2 OF 2) - DESCRIPTION OF CHANGES
EAST BANK WATER TREATMENT PLANT UPGRADE
Item No. | Description | Unit | Unit Price | Original Contract |  | Change Order No. 1 |  | Adjusted Contract |  | Additions
|  |  |  | Quantity | Cost | Quantity | Cost | Quantity | Cost
38 | Structural Steel (Complete) | Lump Sum | 950000 | 1 | 950000 | - | - | 1 | 950000
39 | FRP Products and Fabrications | Lump Sum | 190000 | 1 | 190000 | - | - | 1 | 190000
40 | Painting (Complete) | Lump Sum | 180000 | 1 | 180000 | - | - | 1 | 180000
41 | Relocation of Mechanical Infrastructure Items | Lump Sum | 175000 | 1 | 175000 | 0 | 0 | 1 | 175000
42 | Relocation of Electrical and Instrumentation Infrastructure Items | Lump Sum | 175000 | 1 | 175000 | 0 | 0 | 1 | 175000
43 | Relocation and Rehabilitation of Building Systems | Lump Sum | 175000 | 1 | 175000 | - | - | 1 | 175000
44 | Complete Vertical Turbine Distribution Pump, Can, & Motor System | Ea. | 275000 | 3 | 825000 | - | - | 3 | 825000
45 | Can System with Base Plate for Future Pump | Ea. | 115000 | 3 | 345000 | - | - | 3 | 345000
46 | Complete Vertical Turbine Clearwell Pump & Motor System | Ea. | 210000 | 4 | 840000 | - | - | 4 | 840000
47 | Complete Vertical Turbine Waste Pump & Motor System | Ea. | 350000 | 2 | 700000 | - | - | 2 | 700000
48 | Complete Vertical Turbine Sludge Pump & Motor System | Ea. | 145000 | 2 | 290000 | - | - | 2 | 290000
49 | Chemical Feed and Metering Systems (Complete) | Lump Sum | 752000 | 1 | 752000 | - | - | 1 | 752000
50 | Lift Station (Complete) | Lump Sum | 45000 | 1 | 45000 | - | - | 1 | 45000
51 | Clarifier Unit with Components (Total Avg. Des. Cap.=6.0MGD) | Lump Sum | 1350000 | 1 | 1350000 | - | - | 1 | 1350000
52 | Filter Unit with Components (Total Avg. Des. Cap.=6.0MGD) | Lump Sum | 2156500 | 1 | 2156500 | - | - | 1 | 2156500
53 | 5-Ton Bridge Crane System | Ea. | 23000 | 1 | 23000 | - | - | 1 | 23000
54 | 1-Ton Monorail Hoist System | Ea. | 37500 | 1 | 37500 | - | - | 1 | 37500
55 | 3-Ton Monorail Hoist System | Ea. | 45000 | 1 | 45000 | - | - | 1 | 45000
56 | HVAC System (Plant Control Building) | Lump Sum | 50000 | 1 | 50000 | - | - | 1 | 50000
57 | HVAC System (Chemical Feed Building) | Lump Sum | 35000 | 1 | 35000 | - | - | 1 | 35000
58 | Complete Electrical and Instrumentation Work | Lump Sum | 3750000 | 1 | 3750000 | - | - | 1 | 3750000
59 | Mobilization | Lump Sum | 1200000 | 1 | 1200000 | - | - | 1 | 1200000
60 | General Site Work | Lump Sum | 75000 | 1 | 75000 | - | - | 1 | 75000
61 | Removal, Disposal, and Relocation Work | Lump Sum | 850000 | 1 | 850000 | - | - | 1 | 850000
62 | Plant Control Building | Lump Sum | 285000 | 1 | 285000 | - | - | 1 | 285000
63 | Chemical Feed Building | Lump Sum | 175000 | 1 | 175000 | - | - | 1 | 175000
64 | 18" HDPE Directional Drill Beneath LA 48 | Lump Sum | 125000 | 1 | 125000 | - | - | 1 | 125000
65 | 18" DI Sludge Line Crossing | Lump Sum | 375000 | 1 | 375000 | - | - | 1 | 375000
66 | Entergy Tie-In Costs | Lump Sum | 25000 | 1 | 25000 | - | - | 1 | 25000 | -
67 | Demolish Existing Elevated Walkways and Install New Stairs and Platforms | Lump Sum | 69196.55 | - | - | 1 | 69196.55 | 1 | 69196.55 | 69196.55
|  |  | SUB TOTALS: |  | 26450000 |  |  |  | 26519196.55 | 0
|  |  | RESULTING INCREASE (DECREASE) FOR PROJECT BID: | [5 empty] | 69196.55